HINDRANCE REGISTER

NH-44 Karnataka | 4-Laning KA-03 | Agreement: NHAI/KA/EPC/2025/KA-03

TEST DOCUMENT: Contains overlapping hindrances to test EoT Agent overlap deduction logic

| HR No. | Category | Nature of Hindrance | BoQ Items Blocked | Start Date | End Date | Days | Overlap With | Overlap Days | Net EoT Days | EoT Filed (14d?) | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| HR-001 | Authority Default | GFC Drawing for Pier Cap, Bridge at Km 231 — not issued despite contractor submission on Day 132 | M30 Concrete (Bridges), Pile Foundation | Day 132 (2025-09-12) | Day 146 (2025-09-26) | 14 | — | 0 | 14 | Day 146 (Day 132+14) ✓ ON TIME | CLOSED — EoT 14 days APPROVED |
| HR-002 | Utility Shifting | HT Power Line at Km 234 not shifted by BESCOM — complete blockage of earthwork and sub-base on Km 232–236 | Earthwork, GSB, WMM at Km 232–236 | Day 155 (2025-10-04) | Day 176 (2025-10-25) | 21 | HR-003 | 8 (Days 165–172 overlap) | 13 | Day 169 (Day 155+14) ✓ ON TIME | CLOSED — EoT 13 days APPROVED (8 days deducted as concurrent with HR-003) |
| HR-003 | FM Weather | Abnormal rainfall — IMD certified 310mm/72hr (Day 163). Flood inundation of embankment at Km 225–230. Site access blocked. | All items at Km 225–230 | Day 163 (2025-10-12) | Day 175 (2025-10-24) | 12 | HR-002 | 8 (Days 165–172 overlap) | 4 | Day 170 (Day 163+7) ✓ ON TIME (FM — 7-day window) | CLOSED — FM EoT 4 days APPROVED (8 days deducted concurrent with HR-002) |
| HR-004 | Authority Default | RoW not handed over at Km 238–241.2 (3.2 km). District Collector notice served but acquisition delayed. | Earthwork, GSB, WMM, Drainage at Km 238–241.2 | Day 180 (2025-11-08) | Ongoing | 60+ | HR-005 | TBD | TBD | Day 213 (Day 180+33) ✗ LATE by 19 days — claim at risk | OPEN — EoT application LATE — Authority's Engineer reviewing |
| HR-005 | Indirect Political | District-wide bandh (Day 192) — labour did not report, material trucks blocked. Police FIR obtained. | All items — total site shutdown | Day 192 (2025-11-20) | Day 193 (2025-11-21) | 2 | HR-004 | 2 (full overlap) | 0 | Day 220 (Day 192+28) ✗ FORFEITED — window Day 206 already passed | OPEN — EoT right FORFEITED. 14-day window missed. 0 days eligible. |
| HR-006 | Statutory Clearance | Stage-II Forest Clearance pending from MoEFCC for Km 248–252 (4 km through reserve forest). Work cannot commence in this section. | All items at Km 248–252 | Day 210 (2025-11-28) | Ongoing | 45+ | — | 0 | TBD | Day 224 (Day 210+14) ✓ ON TIME — filed Day 222 | OPEN — EoT pending AE decision. No concurrent hindrance. |
| TOTAL | 6 Hindrances | 3 Closed ¦ 3 Open |  |  |  | 110+ |  | 18 deducted | 35 days | 1 forfeited, 1 late |  |

EoT CALCULATION WORKINGS (for Agent Verification)

The following shows the net EoT calculation that the EoT Agent must replicate, including overlap deductions:

| Hindrance | Gross Days | Overlap Deduction | Net Days Eligible | EoT Status | Clause / Note |
| --- | --- | --- | --- | --- | --- |
| HR-001 (GFC Drawing) | 14 | 0 | 14 | APPROVED | Article 20.2 — Authority default, timely application |
| HR-002 (HT Line) | 21 | 8 (Days 165–172 = HR-003 concurrent) | 13 | APPROVED | Article 20.2 — Utility shifting; overlap deducted per Article 20.3 |
| HR-003 (FM Flood) | 12 | 8 (Days 165–172 = HR-002 concurrent) | 4 | APPROVED | Article 19.4 — FM weather; notice within 7 days; IMD certified |
| HR-004 (RoW) | 60+ | 2 (HR-005 fully contained) | TBD | PENDING (late) | Article 20.2 — EoT filed 19 days late — AE discretion required |
| HR-005 (Bandh) | 2 | 2 (fully within HR-004) | 0 | FORFEITED | EoT window missed AND fully overlaps HR-004 — 0 net days |
| HR-006 (Forest Cl.) | 45+ | 0 | TBD | PENDING | Article 20.2 — Statutory; no concurrent; timely application |
| NET APPROVED EoT (so far) |  | 18 days total | 31 days |  | HR-004 and HR-006 decisions pending AE |

SIGNATURES — JOINT CERTIFICATION

I/We certify that the above hindrances are correctly recorded and the dates of occurrence and removal are accurate to the best of our knowledge.

| Contractor Representative Mr. Suresh Patel / Site Manager Signature: ________________ Date: ________________ | Junior Engineer Er. Anand Sharma (JE Civil) Signature: ________________ Date: ________________ | Assistant Engineer Er. Meera Iyer (AE Civil) Signature: ________________ Date: ________________ |
| --- | --- | --- |