MONTHLY PROGRESS REPORT

NH-44 Karnataka | 4-Laning KA-03 | Month 5 Report

TEST SCENARIO D: FORCE MAJEURE EVENT — Valid IMD-certified flood (Day 145), notice filed Day 150 (within 7 days)

SECTION 1 — PROJECT METADATA

| Project Name | 4-Laning of NH-44 from Km 220 to Km 260 (KA-03) |
| --- | --- |
| Agreement Number | NHAI/KA/EPC/2025/KA-03 |
| Contract Type | EPC — NITI Aayog Model Agreement |
| Contract Value | INR 25,00,00,000 |
| Contractor | M/s. Horizon Infratech Pvt. Ltd. |
| Engineer-in-Charge | Er. Pradeep Nair, Superintending Engineer |
| Reporting Period | 2025-09-01 to 2025-09-30 |
| Day Number (from Appointed Date) | 152 of 730 |
| Scheduled Completion Date | 2027-03-31 |
| Approved EoT Date (if any) | 7 days EoT approved (FM-001) — new M-1 date: Day 211 |
| Revised Completion Date | 2027-04-07 (7 days extended) |

SECTION 2 — PHYSICAL & FINANCIAL PROGRESS

| Parameter | Planned | Actual | Variance | Status |
| --- | --- | --- | --- | --- |
| Physical Progress to Date (%) | 20.8% | 17.2% | -3.6% | AT RISK |
| Cumulative Expenditure (₹ Lakhs) | 528.00 | 442.50 | -85.50 | AT RISK |
| Financial Progress (%) | 21.1% | 17.7% | -3.4% | — |

S-Curve Deviation: -3.6% deviation. Flood event on Day 145 caused 7-day total stoppage. FM notice filed Day 150 (5 days after event — WITHIN 7-day window — VALID).

Recovery Velocity Required (% per day): 0.142% per day (post-FM recovery plan submitted)

Current Velocity (% per day): 0.113% per day (impacted by flood; recovering)

SECTION 3 — BoQ EXECUTION DATA

| BoQ Item | Unit | Total Qty | Prev Cum. | This Month | Cumulative | % Done |
| --- | --- | --- | --- | --- | --- | --- |
| Earthwork Embankment | Cum | 4,50,000 | 66,700 | 14,200 | 80,900 | 18.0% |
| Granular Sub-Base (GSB) | Cum | 85,000 | 3,800 | 1,100 | 4,900 | 5.8% |
| M30 Concrete (Bridges) | Cum | 12,000 | 1,310 | 180 | 1,490 | 12.4% |
| Pile Foundation | RM | 4,200 | 780 | 80 | 860 | 20.5% |
| WMM | Cum | 72,000 | 0 | 0 | 0 | 0.0% |

SECTION 4 — MATERIAL RECONCILIATION

| Material | Opening | Received | Consumed | Closing | Theoretical |
| --- | --- | --- | --- | --- | --- |
| Cement (bags) | 1,660 | 2,200 | 2,100 | 1,760 | 2,080 |
| Steel (MT) | 18 | 22 | 21 | 19 | 21 |
| Bitumen (MT) | 0 | 0 | 0 | 0 | 0 |

SECTION 5 — LABOUR & MACHINERY

| Planned Skilled Labour (daily avg) | 85 |
| --- | --- |
| Actual Skilled Labour (daily avg) | 72 |
| Planned Unskilled Labour (daily avg) | 210 |
| Actual Unskilled Labour (daily avg) | 161 |
| Key Machinery Deployed | 3 Excavators, 2 Tipper Trucks, 1 Concrete Batching Plant — all recovered post-flood |
| Machinery Idle Days | 7 days (flood-related — FM period) |

SECTION 6 — QUALITY ASSURANCE

| Test Type | Material | Conducted | Passed | Failed | Remarks |
| --- | --- | --- | --- | --- | --- |
| Cube Strength (7-day) | M30 Concrete | 3 | 3 | 0 | All passed |
| Field Density Test | Embankment Soil | 3 | 3 | 0 | All ≥ 97% MDD |
| Flood Damage Assessment | GSB layers Km 225–228 | 1 | 0 | 1 | 2 GSB layers damaged by inundation — repair NCR-004 issued |

| NCRs Issued This Month | 1 |
| --- | --- |
| NCRs Pending Closure | 1 |
| RFIs Submitted | 3 |
| RFIs Pending Approval | 2 |

SECTION 7 — EXTERNAL DISRUPTIONS & HINDRANCE DATA

| Working Days in Month | 30 |
| --- | --- |
| Days Lost to Rainfall | 18 |
| Days Lost to Other Hindrances | 7 |
| Daily Rainfall (avg mm) | 28.4 |
| Cumulative Rainfall this Month (mm) | 512.0 |
| Active Force Majeure Claim | FM-001 — VALID. Flood on Day 145 (2025-09-13). IMD certificate: 312mm in 24hrs (3.8 SD above 30-year normal). Notice filed Day 150 (2025-09-18) — within 7-day window. |
| Weather Anomaly Score (IMD) | 0.88 — EXCEEDS FM THRESHOLD (0.75). IMD certificate obtained. FM Relief: 7 days EoT approved. |

SECTION 8 — RIGHT OF WAY & UTILITIES

| Total RoW Required (km) | 40.0 |
| --- | --- |
| RoW Handed Over (km) | 38.5 |
| RoW Pending (km) | 1.5 |
| Pending Chainage | Km 241.2 to Km 242.7 |
| HT Power Lines Shifted | Yes |
| Utility Shifting Status | All utilities clear except 1 water main — not blocking work |
| Tree Felling Clearance | Yes |

SECTION 9 — GFC DRAWING STATUS

| Total GFC Drawings Required | 48 |
| --- | --- |
| GFC Drawings Approved | 34 |
| GFC Drawings Pending | 14 |
| Critical Pending Drawing | Bridge at Km 231 expansion joint — approved 2025-09-12, work proceeding |

SECTION 10 — RA BILL & PAYMENT STATUS

| RA Bill Number | RA-05 |
| --- | --- |
| RA Bill Amount (₹ Lakhs) | 61.20 Lakhs |
| RA Bill Submitted Date | 2025-10-05 |
| Previous Bill Payment Received | Yes |
| Previous Bill Payment Date | 2025-09-25 |
| Payment Delay (days) | 0 |
| Cumulative LD Deducted (₹) | ₹0 (no milestone missed — FM period excused) |
| LD Cap Utilised (%) | 0.0% |

SECTION 11 — ACTIVE COMPLIANCE EVENTS

- [LOW] C11_FM001: FM-001 VALID — 7-day EoT approved. Notice within window. IMD certified 312mm/24hr. — Article 19.2.1

- [MEDIUM] C07b: NCR-004: GSB damage at Km 225–228 due to flood inundation — repair in progress — Article 11.14

SECTION 12 — RISK ASSESSMENT

| Current Risk Score | 0.38 / 1.00 |
| --- | --- |
| Risk Label | MEDIUM |
| Top Risk Factor #1 | Post-FM recovery: 7 days lost must be made up — velocity slightly below target |
| Top Risk Factor #2 | NCR-004 for flood-damaged GSB layers — must be repaired before bituminous layers |
| Top Risk Factor #3 | Monsoon season continues — monitor for further FM events |
| Forecast: Next Milestone Achievement | M-1 (revised Day 211) — ACHIEVABLE if labour ramps back to 85/day within 2 weeks |

SECTION 13 — RECOMMENDATIONS & ACTIONS

- FM-001 relief of 7 days EoT is formally approved — revised M-1 date is Day 211.

- File weekly FM status updates as required by Article 19.2.3 until site fully restored.

- Repair flood-damaged GSB layers (NCR-004) within 21 days before paving commences.

- Ramp labour back to 85 skilled workers within 14 days — current at 72.

- Document all additional costs from flood (pumping, repair, delay costs) — eligible for reimbursement if FM is Political Event category (verify with legal team).

- Monitor IMD forecasts for remainder of monsoon — next FM threshold event should be reported within 7 days.

SECTION 14 — CERTIFICATION

| Reported By | Er. Anand Sharma |
| --- | --- |
| Designation | Junior Engineer (Civil) |
| Verified By (AE/JE) | Er. Meera Iyer (AE) |
| Report Date | 2025-10-03 |
| Engineer-in-Charge Approval | Pending / Approved |