MONTHLY PROGRESS REPORT

NH-44 Karnataka | 4-Laning KA-03 | Month 6 Report

TEST SCENARIO E: INVALID FM CLAIM + LATE EoT APPLICATION — Notice 12 days late (forfeited), EoT 18 days late (forfeit risk)

SECTION 1 — PROJECT METADATA

| Project Name | 4-Laning of NH-44 from Km 220 to Km 260 (KA-03) |
| --- | --- |
| Agreement Number | NHAI/KA/EPC/2025/KA-03 |
| Contract Type | EPC — NITI Aayog Model Agreement |
| Contract Value | INR 25,00,00,000 |
| Contractor | M/s. Horizon Infratech Pvt. Ltd. |
| Engineer-in-Charge | Er. Pradeep Nair, Superintending Engineer |
| Reporting Period | 2025-10-01 to 2025-10-31 |
| Day Number (from Appointed Date) | 183 of 730 |
| Scheduled Completion Date | 2027-03-31 |
| Approved EoT Date (if any) | — |
| Revised Completion Date | — |

SECTION 2 — PHYSICAL & FINANCIAL PROGRESS

| Parameter | Planned | Actual | Variance | Status |
| --- | --- | --- | --- | --- |
| Physical Progress to Date (%) | 25.1% | 19.8% | -5.3% | DELAYED |
| Cumulative Expenditure (₹ Lakhs) | 636.00 | 512.50 | -123.50 | AT RISK |
| Financial Progress (%) | 25.4% | 20.5% | -4.9% | — |

S-Curve Deviation: -5.3% deviation. Contractor claims 21-day delay due to rainfall (Day 162) but FM notice filed on Day 174 — 12 days after event, FORFEITING all FM relief.

Recovery Velocity Required (% per day): 0.165% per day

Current Velocity (% per day): 0.107% per day

SECTION 3 — BoQ EXECUTION DATA

| BoQ Item | Unit | Total Qty | Prev Cum. | This Month | Cumulative | % Done |
| --- | --- | --- | --- | --- | --- | --- |
| Earthwork Embankment | Cum | 4,50,000 | 80,900 | 10,200 | 91,100 | 20.2% |
| Granular Sub-Base (GSB) | Cum | 85,000 | 4,900 | 600 | 5,500 | 6.5% |
| M30 Concrete (Bridges) | Cum | 12,000 | 1,490 | 140 | 1,630 | 13.6% |
| Pile Foundation | RM | 4,200 | 860 | 60 | 920 | 21.9% |
| WMM | Cum | 72,000 | 0 | 0 | 0 | 0.0% |

SECTION 4 — MATERIAL RECONCILIATION

| Material | Opening | Received | Consumed | Closing | Theoretical |
| --- | --- | --- | --- | --- | --- |
| Cement (bags) | 1,760 | 1,900 | 1,980 | 1,680 | 2,000 |
| Steel (MT) | 19 | 18 | 20 | 17 | 20 |
| Bitumen (MT) | 0 | 0 | 0 | 0 | 0 |

SECTION 5 — LABOUR & MACHINERY

| Planned Skilled Labour (daily avg) | 85 |
| --- | --- |
| Actual Skilled Labour (daily avg) | 58 |
| Planned Unskilled Labour (daily avg) | 210 |
| Actual Unskilled Labour (daily avg) | 132 |
| Key Machinery Deployed | 2 Excavators, 2 Tipper Trucks, 1 Concrete Batching Plant |
| Machinery Idle Days | 21 days (claimed as FM — INVALID due to late notice) |

SECTION 6 — QUALITY ASSURANCE

| Test Type | Material | Conducted | Passed | Failed | Remarks |
| --- | --- | --- | --- | --- | --- |
| Cube Strength (7-day) | M30 Concrete | 3 | 3 | 0 | All passed |
| Field Density Test | Embankment Soil | 2 | 2 | 0 | All ≥ 97% MDD |

| NCRs Issued This Month | 0 |
| --- | --- |
| NCRs Pending Closure | 1 |
| RFIs Submitted | 2 |
| RFIs Pending Approval | 2 |

SECTION 7 — EXTERNAL DISRUPTIONS & HINDRANCE DATA

| Working Days in Month | 31 |
| --- | --- |
| Days Lost to Rainfall | 16 |
| Days Lost to Other Hindrances | 21 |
| Daily Rainfall (avg mm) | 22.1 |
| Cumulative Rainfall this Month (mm) | 384.0 |
| Active Force Majeure Claim | FM-002 — INVALID. Rainfall event Day 162 (2025-10-01). FM notice filed Day 174 (2025-10-13) — 12 DAYS AFTER EVENT. 7-day notice window EXPIRED. All FM relief FORFEITED per Article 19.2.1. |
| Weather Anomaly Score (IMD) | 0.62 — Below FM threshold (0.75). Even if notice were timely, FM would require IMD anomaly score ≥ 0.75. |

SECTION 8 — RIGHT OF WAY & UTILITIES

| Total RoW Required (km) | 40.0 |
| --- | --- |
| RoW Handed Over (km) | 36.8 |
| RoW Pending (km) | 3.2 |
| Pending Chainage | Km 238.0 to Km 241.2 |
| HT Power Lines Shifted | No — 2 HT lines pending |
| Utility Shifting Status | BESCOM: 45-day estimate for HT shifting — hindrance HR-003 logged Day 165 |
| Tree Felling Clearance | Yes |

SECTION 9 — GFC DRAWING STATUS

| Total GFC Drawings Required | 48 |
| --- | --- |
| GFC Drawings Approved | 31 |
| GFC Drawings Pending | 17 |
| Critical Pending Drawing | Pier cap for Bridge Km 231 — pending 51 days (hindrance HR-002 logged Day 132) |

SECTION 10 — RA BILL & PAYMENT STATUS

| RA Bill Number | RA-06 |
| --- | --- |
| RA Bill Amount (₹ Lakhs) | 42.80 Lakhs |
| RA Bill Submitted Date | 2025-11-05 |
| Previous Bill Payment Received | Yes |
| Previous Bill Payment Date | 2025-10-30 |
| Payment Delay (days) | 0 |
| Cumulative LD Deducted (₹) | ₹0 (M-1 not yet due — Day 204 is 21 days away) |
| LD Cap Utilised (%) | 0.0% (M-1 LD will begin accruing in 21 days if not achieved) |

SECTION 11 — ACTIVE COMPLIANCE EVENTS

- [HIGH] C11a: FM-002 REJECTED — notice filed 12 days after event. 7-day window expired per Article 19.2.1. All FM relief forfeited. — Article 19.2.1

- [HIGH] C10a: EoT for HR-002 (GFC delay since Day 132): Application filed Day 150 — 18 days late. Claim may be forfeited under Article 20.2. — Article 20.2

- [HIGH] C10b: EoT for HR-003 (HT line delay since Day 165): Application not yet filed. Deadline Day 179 ALREADY PASSED — EoT right forfeited. — Article 20.2

- [MEDIUM] C06: Labour at 68.2% of planned — insufficient for M-1 recovery in 21 days — Article 10.1.1

- [LOW] C03_M1_WARN: WARNING: M-1 due Day 204 — 21 days away. Current trajectory projects 19.8% by Day 204 (shortfall 0.2%). — Article 10.3.1

SECTION 12 — RISK ASSESSMENT

| Current Risk Score | 0.68 / 1.00 |
| --- | --- |
| Risk Label | HIGH |
| Top Risk Factor #1 | FM-002 rejected — 21 days of claimed delay will now count as contractor's fault, LD will apply |
| Top Risk Factor #2 | EoT for HR-003 forfeited — contractor loses 15+ days of legitimate extension right |
| Top Risk Factor #3 | M-1 marginally at risk — 19.8% vs 20% required by Day 204 |
| Forecast: Next Milestone Achievement | M-1 (Day 204) — MARGINAL. 0.2% shortfall projected. Any further disruption = miss. |

SECTION 13 — RECOMMENDATIONS & ACTIONS

- CRITICAL LESSON: FM-002 is INVALID due to 12-day late notice. The 7-day rule in Article 19.2.1 is absolute — contractor must track this date rigorously.

- CRITICAL LESSON: EoT for HR-003 right forfeited — 14-day rule in Article 20.2 must be monitored from day of hindrance, not from when it becomes convenient.

- Immediately escalate HT line issue (HR-003) via Authority's Engineer — even without EoT right, Authority delay is documented.

- Sprint to achieve 20% by Day 204: deploy all available resources to M-1 target activities.

- Train site team on FM notice and EoT application deadlines — these procedural failures are causing significant legal and financial damage.

- File EoT application for HR-002 formally — even if late, document the claim and let Authority's Engineer decide on leniency.

SECTION 14 — CERTIFICATION

| Reported By | Er. Anand Sharma |
| --- | --- |
| Designation | Junior Engineer (Civil) |
| Verified By (AE/JE) | Er. Meera Iyer (AE) |
| Report Date | 2025-11-03 |
| Engineer-in-Charge Approval | Pending / Approved |