MONTHLY PROGRESS REPORT

NH-44 Karnataka | 4-Laning KA-03 | Month 7 Report

TEST SCENARIO B: AT-RISK PROJECT — Milestone-I just missed, LD accruing, slow recovery

SECTION 1 — PROJECT METADATA

| Project Name | 4-Laning of NH-44 from Km 220 to Km 260 (KA-03) |
| --- | --- |
| Agreement Number | NHAI/KA/EPC/2025/KA-03 |
| Contract Type | EPC — NITI Aayog Model Agreement |
| Contract Value | INR 25,00,00,000 |
| Contractor | M/s. Horizon Infratech Pvt. Ltd. |
| Engineer-in-Charge | Er. Pradeep Nair, Superintending Engineer |
| Reporting Period | 2025-11-01 to 2025-11-30 |
| Day Number (from Appointed Date) | 214 of 730 (M-1 was due Day 204 — 10 days ago) |
| Scheduled Completion Date | 2027-03-31 |
| Approved EoT Date (if any) | — |
| Revised Completion Date | — |

SECTION 2 — PHYSICAL & FINANCIAL PROGRESS

| Parameter | Planned | Actual | Variance | Status |
| --- | --- | --- | --- | --- |
| Physical Progress to Date (%) | 29.3% | 18.4% | -10.9% | DELAYED |
| Cumulative Expenditure (₹ Lakhs) | 742.00 | 612.50 | -129.50 | AT RISK |
| Financial Progress (%) | 29.7% | 24.5% | -5.2% | — |

S-Curve Deviation: -10.9% BELOW planned curve. Milestone-I missed by 10 days. Required recovery velocity is 0.187%/day vs current 0.086%/day.

Recovery Velocity Required (% per day): 0.187% per day (to recover M-2 by Day 401)

Current Velocity (% per day): 0.086% per day (INSUFFICIENT)

SECTION 3 — BoQ EXECUTION DATA

| BoQ Item | Unit | Total Qty | Prev Cum. | This Month | Cumulative | % Done |
| --- | --- | --- | --- | --- | --- | --- |
| Earthwork Embankment | Cum | 4,50,000 | 66,700 | 18,100 | 84,800 | 18.8% |
| Granular Sub-Base (GSB) | Cum | 85,000 | 3,800 | 1,200 | 5,000 | 5.9% |
| M30 Concrete (Bridges) | Cum | 12,000 | 1,310 | 290 | 1,600 | 13.3% |
| Pile Foundation | RM | 4,200 | 780 | 120 | 900 | 21.4% |
| WMM | Cum | 72,000 | 0 | 0 | 0 | 0.0% |

SECTION 4 — MATERIAL RECONCILIATION

| Material | Opening | Received | Consumed | Closing | Theoretical |
| --- | --- | --- | --- | --- | --- |
| Cement (bags) | 1,660 | 3,800 | 4,100 | 1,360 | 4,150 |
| Steel (MT) | 18 | 28 | 31 | 15 | 32 |
| Bitumen (MT) | 0 | 0 | 0 | 0 | 0 |

SECTION 5 — LABOUR & MACHINERY

| Planned Skilled Labour (daily avg) | 85 |
| --- | --- |
| Actual Skilled Labour (daily avg) | 54 |
| Planned Unskilled Labour (daily avg) | 210 |
| Actual Unskilled Labour (daily avg) | 118 |
| Key Machinery Deployed | 2 Excavators (2 broken down), 2 Tipper Trucks, 1 Concrete Batching Plant |
| Machinery Idle Days | 14 days (2 excavators under repair since Day 200) |

SECTION 6 — QUALITY ASSURANCE

| Test Type | Material | Conducted | Passed | Failed | Remarks |
| --- | --- | --- | --- | --- | --- |
| Cube Strength (7-day) | M30 Concrete | 4 | 3 | 1 | 1 batch: 17.8 MPa — NCR-002 issued |
| Field Density Test | Embankment Soil | 3 | 2 | 1 | 1 layer: 94.2% MDD — below 97% — NCR-003 issued |
| Slump Test | M30 Concrete | 12 | 12 | 0 | Within range |

| NCRs Issued This Month | 2 |
| --- | --- |
| NCRs Pending Closure | 3 |
| RFIs Submitted | 2 |
| RFIs Pending Approval | 3 |

SECTION 7 — EXTERNAL DISRUPTIONS & HINDRANCE DATA

| Working Days in Month | 30 |
| --- | --- |
| Days Lost to Rainfall | 6 |
| Days Lost to Other Hindrances | 14 |
| Daily Rainfall (avg mm) | 11.2 |
| Cumulative Rainfall this Month (mm) | 67.2 |
| Active Force Majeure Claim | None — rainfall within seasonal norms |
| Weather Anomaly Score (IMD) | 0.28 — Within Normal Range (not FM-eligible) |

SECTION 8 — RIGHT OF WAY & UTILITIES

| Total RoW Required (km) | 40.0 |
| --- | --- |
| RoW Handed Over (km) | 36.8 |
| RoW Pending (km) | 3.2 |
| Pending Chainage | Km 238.0 to Km 241.2 — District Collector notice issued |
| HT Power Lines Shifted | No — 2 HT lines pending at Km 234 and Km 238 |
| Utility Shifting Status | BESCOM advised 60-day timeline for HT line shifting — critical path impact |
| Tree Felling Clearance | Yes |

SECTION 9 — GFC DRAWING STATUS

| Total GFC Drawings Required | 48 |
| --- | --- |
| GFC Drawings Approved | 31 |
| GFC Drawings Pending | 17 |
| Critical Pending Drawing | Pier cap design for Bridge at Km 231 — submitted Day 182 (32 days pending) |

SECTION 10 — RA BILL & PAYMENT STATUS

| RA Bill Number | RA-07 |
| --- | --- |
| RA Bill Amount (₹ Lakhs) | 48.50 Lakhs |
| RA Bill Submitted Date | 2025-12-05 |
| Previous Bill Payment Received | Yes (delayed) |
| Previous Bill Payment Date | 2025-11-18 |
| Payment Delay (days) | 18 |
| Cumulative LD Deducted (₹) | ₹2,50,000 (for M-1 delay — 10 days × ₹25,000/day) |
| LD Cap Utilised (%) | 1.0% |

SECTION 11 — ACTIVE COMPLIANCE EVENTS

- [HIGH] C03_M1: Milestone-I Missed — Day 204. Actual 18.4% vs required 20% — Article 10.3.1

- [HIGH] C07a: NCR-002: Concrete cube strength failure (17.8 MPa) — Article 11.14

- [HIGH] C07b: NCR-003: Embankment density failure (94.2% < 97% MDD) — Article 11.14

- [MEDIUM] C06: Labour utilisation at 63.5% — significantly below planned level — Article 10.1.1

- [MEDIUM] C08: 17 GFC Drawings pending — critical path blockage identified — Article 20

- [LOW] C13: RA-06 Bill payment delayed 18 days — authority default risk — Article 22.2

SECTION 12 — RISK ASSESSMENT

| Current Risk Score | 0.74 / 1.00 |
| --- | --- |
| Risk Label | HIGH |
| Top Risk Factor #1 | S-curve deviation -10.9% — widening gap, no sign of recovery |
| Top Risk Factor #2 | Machinery breakdown (2 excavators) — 14 idle days severely impacted earthwork |
| Top Risk Factor #3 | 3 open NCRs blocking payment certification for affected works |
| Forecast: Next Milestone Achievement | M-1 formally missed. M-2 (Day 401) at HIGH risk — requires doubling of current velocity |

SECTION 13 — RECOMMENDATIONS & ACTIONS

- URGENT: Repair or replace the 2 broken excavators immediately — earthwork is the critical path.

- URGENT: Increase skilled labour to at least 85/day — current level (54) is 36% below plan.

- Issue formal hindrance entry for HT line delay at Km 234 and 238 — file EoT application within 14 days.

- Escalate GFC drawing approval for Bridge at Km 231 to Authority's Engineer — 32 days pending is unacceptable.

- Close NCR-002 and NCR-003 within 15 days to unblock payment certification.

- Raise formal dispute on delayed RA-06 payment — 18 days late, interest applicable per Article 22.2.

- LD accruing at ₹25,000/day — catch-up refund possible if M-SCD achieved on time (Article 10.3.3).

SECTION 14 — CERTIFICATION

| Reported By | Er. Anand Sharma |
| --- | --- |
| Designation | Junior Engineer (Civil) |
| Verified By (AE/JE) | Er. Meera Iyer (AE) |
| Report Date | 2025-12-03 |
| Engineer-in-Charge Approval | Pending / Approved |