MONTHLY PROGRESS REPORT

NH-44 Karnataka | 4-Laning KA-03 | Month 14 Report

TEST SCENARIO C: DEFAULTING PROJECT — M1+M2 missed, LD at 62% cap, NCRs unresolved, termination risk

SECTION 1 — PROJECT METADATA

| Project Name | 4-Laning of NH-44 from Km 220 to Km 260 (KA-03) |
| --- | --- |
| Agreement Number | NHAI/KA/EPC/2025/KA-03 |
| Contract Type | EPC — NITI Aayog Model Agreement |
| Contract Value | INR 25,00,00,000 |
| Contractor | M/s. Horizon Infratech Pvt. Ltd. |
| Engineer-in-Charge | Er. Pradeep Nair, Superintending Engineer |
| Reporting Period | 2026-06-01 to 2026-06-30 |
| Day Number (from Appointed Date) | 426 of 730 (M-2 due Day 401 — 25 days ago) |
| Scheduled Completion Date | 2027-03-31 |
| Approved EoT Date (if any) | — |
| Revised Completion Date | — |

SECTION 2 — PHYSICAL & FINANCIAL PROGRESS

| Parameter | Planned | Actual | Variance | Status |
| --- | --- | --- | --- | --- |
| Physical Progress to Date (%) | 58.4% | 34.2% | -24.2% | DELAYED |
| Cumulative Expenditure (₹ Lakhs) | 1,478.00 | 1,021.50 | -456.50 | DELAYED |
| Financial Progress (%) | 59.1% | 40.9% | -18.2% | — |

S-Curve Deviation: -24.2% CRITICAL deviation. Both M-1 and M-2 missed. Required velocity to achieve SCD is 0.302%/day — 4.5× current rate. Recovery near-impossible.

Recovery Velocity Required (% per day): 0.302% per day (to achieve SCD Day 730)

Current Velocity (% per day): 0.067% per day (CRITICAL — 22% of required)

SECTION 3 — BoQ EXECUTION DATA

| BoQ Item | Unit | Total Qty | Prev Cum. | This Month | Cumulative | % Done |
| --- | --- | --- | --- | --- | --- | --- |
| Earthwork Embankment | Cum | 4,50,000 | 84,800 | 8,200 | 93,000 | 20.7% |
| Granular Sub-Base (GSB) | Cum | 85,000 | 5,000 | 800 | 5,800 | 6.8% |
| M30 Concrete (Bridges) | Cum | 12,000 | 1,600 | 180 | 1,780 | 14.8% |
| Pile Foundation | RM | 4,200 | 900 | 60 | 960 | 22.9% |
| WMM | Cum | 72,000 | 0 | 0 | 0 | 0.0% |

SECTION 4 — MATERIAL RECONCILIATION

| Material | Opening | Received | Consumed | Closing | Theoretical |
| --- | --- | --- | --- | --- | --- |
| Cement (bags) | 1,360 | 1,200 | 1,400 | 1,160 | 1,450 |
| Steel (MT) | 15 | 12 | 14 | 13 | 15 |
| Bitumen (MT) | 0 | 0 | 0 | 0 | 0 |

SECTION 5 — LABOUR & MACHINERY

| Planned Skilled Labour (daily avg) | 85 |
| --- | --- |
| Actual Skilled Labour (daily avg) | 31 |
| Planned Unskilled Labour (daily avg) | 210 |
| Actual Unskilled Labour (daily avg) | 62 |
| Key Machinery Deployed | 1 Excavator (only 1 operational), 1 Tipper Truck |
| Machinery Idle Days | 21 days — near-abandonment level |

SECTION 6 — QUALITY ASSURANCE

| Test Type | Material | Conducted | Passed | Failed | Remarks |
| --- | --- | --- | --- | --- | --- |
| Cube Strength (7-day) | M30 Concrete | 2 | 1 | 1 | NCR-006 issued — pending 45 days |
| Field Density Test | Embankment Soil | 1 | 0 | 1 | NCR-007 issued — pending 22 days |

| NCRs Issued This Month | 2 |
| --- | --- |
| NCRs Pending Closure | 7 |
| RFIs Submitted | 1 |
| RFIs Pending Approval | 6 |

SECTION 7 — EXTERNAL DISRUPTIONS & HINDRANCE DATA

| Working Days in Month | 30 |
| --- | --- |
| Days Lost to Rainfall | 8 |
| Days Lost to Other Hindrances | 18 |
| Daily Rainfall (avg mm) | 14.8 |
| Cumulative Rainfall this Month (mm) | 92.0 |
| Active Force Majeure Claim | FM-002 (INVALID — notice filed 12 days after event, forfeited) |
| Weather Anomaly Score (IMD) | 0.41 — Above normal but below FM threshold (0.75) |

SECTION 8 — RIGHT OF WAY & UTILITIES

| Total RoW Required (km) | 40.0 |
| --- | --- |
| RoW Handed Over (km) | 35.2 |
| RoW Pending (km) | 4.8 |
| Pending Chainage | Km 236.0–238.0, Km 241.2–244.0 — both in dispute |
| HT Power Lines Shifted | No — 4 HT lines still pending |
| Utility Shifting Status | CRITICAL — Km 236–238 completely blocked by HT lines and water main |
| Tree Felling Clearance | Yes |

SECTION 9 — GFC DRAWING STATUS

| Total GFC Drawings Required | 48 |
| --- | --- |
| GFC Drawings Approved | 28 |
| GFC Drawings Pending | 20 |
| Critical Pending Drawing | MULTIPLE critical drawings pending 60+ days — authority under notice |

SECTION 10 — RA BILL & PAYMENT STATUS

| RA Bill Number | RA-14 |
| --- | --- |
| RA Bill Amount (₹ Lakhs) | 22.10 Lakhs |
| RA Bill Submitted Date | 2026-07-05 |
| Previous Bill Payment Received | Yes (delayed) |
| Previous Bill Payment Date | 2026-06-28 |
| Payment Delay (days) | 42 |
| Cumulative LD Deducted (₹) | ₹1,55,00,000 (M-1: ₹55L + M-2: ₹1,00,00,000 — 25 days × ₹4,00,000/day) |
| LD Cap Utilised (%) | 62.0% — WARNING: 38% remaining before Contractor Default |

SECTION 11 — ACTIVE COMPLIANCE EVENTS

- [CRITICAL] C04: LD Cap at 62% — Default imminent if trajectory continues — Article 10.3.2

- [CRITICAL] C03_M2: Milestone-II Missed — Day 401. Actual 34.2% vs required 50% — Article 10.3.1

- [HIGH] C03_M1: Milestone-I Missed (ongoing — not recovered) — Article 10.3.1

- [HIGH] C07b: 7 NCRs pending closure — oldest is 78 days old (NCR-001) — Article 11.14

- [HIGH] C11a: FM-002 REJECTED — notice filed 12 days after event (7-day window missed) — Article 19.2.1

- [HIGH] C15: De-mobilisation signals detected — 1 excavator, 31 workers vs 85 planned — Article 23.1.1(b)

- [MEDIUM] C13: RA-13 payment delayed 42 days — authority default risk — Article 22.2

- [MEDIUM] C10: EoT application for HR-004 filed 19 days late — claim may be forfeited — CPWD Clause 5

SECTION 12 — RISK ASSESSMENT

| Current Risk Score | 0.94 / 1.00 |
| --- | --- |
| Risk Label | CRITICAL |
| Top Risk Factor #1 | S-curve deviation -24.2% — recovery mathematically near-impossible at current velocity |
| Top Risk Factor #2 | LD cap at 62% — 25 more days of M-2 delay will push to 100% cap = automatic Contractor Default |
| Top Risk Factor #3 | Effective de-mobilisation: 1 excavator, 31 workers — signals abandonment |
| Forecast: Next Milestone Achievement | CRITICAL: SCD will be missed by estimated 180+ days. LD cap exhaustion projected at Day 466. |

SECTION 13 — RECOMMENDATIONS & ACTIONS

- CRITICAL: Issue Notice of Intent to Terminate under Article 23.1.2 — provide 60-day cure period.

- CRITICAL: Invite counter-proposals from contractor on recovery plan — require submission within 14 days.

- URGENT: Encash Performance Security pre-emptively if contractor fails to submit recovery plan.

- Reject FM-002 claim formally — 12-day late notice forfeits all relief under Article 19.2.1.

- Issue formal Default Notice for NCR-001 (78 days old) — arrange third-party rectification.

- Begin parallel procurement process for completion agency to be ready upon termination.

- Note: Authority also in default on payment (42-day delay) — clear this to avoid counter-claim.

SECTION 14 — CERTIFICATION

| Reported By | Er. Anand Sharma |
| --- | --- |
| Designation | Junior Engineer (Civil) |
| Verified By (AE/JE) | Er. Meera Iyer (AE) |
| Report Date | 2026-07-02 |
| Engineer-in-Charge Approval | Pending / Approved |