MONTHLY PROGRESS REPORT

NH-44 Karnataka | 4-Laning KA-03 | Month 22 Report

TEST SCENARIO F: NEAR-COMPLETION — Early completion bonus eligible, catch-up refund triggered, punch list phase

SECTION 1 — PROJECT METADATA

| Project Name | 4-Laning of NH-44 from Km 220 to Km 260 (KA-03) |
| --- | --- |
| Agreement Number | NHAI/KA/EPC/2025/KA-03 |
| Contract Type | EPC — NITI Aayog Model Agreement |
| Contract Value | INR 25,00,00,000 |
| Contractor | M/s. Horizon Infratech Pvt. Ltd. |
| Engineer-in-Charge | Er. Pradeep Nair, Superintending Engineer |
| Reporting Period | 2027-01-01 to 2027-01-31 |
| Day Number (from Appointed Date) | 672 of 730 (58 days before SCD) |
| Scheduled Completion Date | 2027-03-31 |
| Approved EoT Date (if any) | 7 days (FM-001, Month 5) — already absorbed into schedule |
| Revised Completion Date | 2027-04-07 (extended by FM EoT) — project completing before even original SCD |

SECTION 2 — PHYSICAL & FINANCIAL PROGRESS

| Parameter | Planned | Actual | Variance | Status |
| --- | --- | --- | --- | --- |
| Physical Progress to Date (%) | 92.1% | 97.8% | +5.7% | ON TRACK |
| Cumulative Expenditure (₹ Lakhs) | 2,336.00 | 2,298.50 | -37.50 | ON TRACK |
| Financial Progress (%) | 93.4% | 91.9% | -1.5% | — |

S-Curve Deviation: +5.7% ahead of planned curve. Completion projected Day 698 — 32 days before SCD. Early completion bonus eligible.

Recovery Velocity Required (% per day): N/A — Ahead of schedule

Current Velocity (% per day): 0.121% per day (punch list and finishing phase)

SECTION 3 — BoQ EXECUTION DATA

| BoQ Item | Unit | Total Qty | Prev Cum. | This Month | Cumulative | % Done |
| --- | --- | --- | --- | --- | --- | --- |
| Earthwork Embankment | Cum | 4,50,000 | 4,48,200 | 1,800 | 4,50,000 | 100.0% |
| Granular Sub-Base (GSB) | Cum | 85,000 | 84,100 | 900 | 85,000 | 100.0% |
| M30 Concrete (Bridges) | Cum | 12,000 | 11,820 | 180 | 12,000 | 100.0% |
| Pile Foundation | RM | 4,200 | 4,200 | 0 | 4,200 | 100.0% |
| DBM + BC (Bituminous) | MT | 50,000 | 48,600 | 1,400 | 50,000 | 100.0% |

SECTION 4 — MATERIAL RECONCILIATION

| Material | Opening | Received | Consumed | Closing | Theoretical |
| --- | --- | --- | --- | --- | --- |
| Cement (bags) | 1,200 | 200 | 380 | 1,020 | 400 |
| Steel (MT) | 8 | 2 | 4 | 6 | 4 |
| Bitumen (MT) | 120 | 48 | 62 | 106 | 60 |

SECTION 5 — LABOUR & MACHINERY

| Planned Skilled Labour (daily avg) | 60 |
| --- | --- |
| Actual Skilled Labour (daily avg) | 58 |
| Planned Unskilled Labour (daily avg) | 120 |
| Actual Unskilled Labour (daily avg) | 115 |
| Key Machinery Deployed | 2 Excavators, 2 Tipper Trucks, 1 Paver Finisher (punch list works) |
| Machinery Idle Days | 0 days |

SECTION 6 — QUALITY ASSURANCE

| Test Type | Material | Conducted | Passed | Failed | Remarks |
| --- | --- | --- | --- | --- | --- |
| Core Density (Bituminous) | BC Wearing Course | 12 | 12 | 0 | All ≥ 92% Marshall Density |
| Cube Strength (28-day) | M30 Concrete | 4 | 4 | 0 | All ≥ 34 MPa — final bridge checks |
| Roughness Test (IRI) | NH-44 Carriageway | 40 | 38 | 2 | 2 sections IRI > 2.5 m/km — resurfacing ordered |

| NCRs Issued This Month | 2 |
| --- | --- |
| NCRs Pending Closure | 2 |
| RFIs Submitted | 6 |
| RFIs Pending Approval | 1 |

SECTION 7 — EXTERNAL DISRUPTIONS & HINDRANCE DATA

| Working Days in Month | 31 |
| --- | --- |
| Days Lost to Rainfall | 1 |
| Days Lost to Other Hindrances | 0 |
| Daily Rainfall (avg mm) | 1.2 |
| Cumulative Rainfall this Month (mm) | 8.4 |
| Active Force Majeure Claim | None |
| Weather Anomaly Score (IMD) | 0.02 — Negligible |

SECTION 8 — RIGHT OF WAY & UTILITIES

| Total RoW Required (km) | 40.0 |
| --- | --- |
| RoW Handed Over (km) | 40.0 |
| RoW Pending (km) | 0.0 |
| Pending Chainage | None — all RoW handed over |
| HT Power Lines Shifted | Yes |
| Utility Shifting Status | All utilities shifted — clear |
| Tree Felling Clearance | Yes |

SECTION 9 — GFC DRAWING STATUS

| Total GFC Drawings Required | 48 |
| --- | --- |
| GFC Drawings Approved | 48 |
| GFC Drawings Pending | 0 |
| Critical Pending Drawing | All 48 GFC drawings approved — no pending drawings |

SECTION 10 — RA BILL & PAYMENT STATUS

| RA Bill Number | RA-22 |
| --- | --- |
| RA Bill Amount (₹ Lakhs) | 38.20 Lakhs (punch list works) |
| RA Bill Submitted Date | 2027-02-05 |
| Previous Bill Payment Received | Yes |
| Previous Bill Payment Date | 2027-01-20 |
| Payment Delay (days) | 0 |
| Cumulative LD Deducted (₹) | ₹55,00,000 (M-1 LD from Month 7, subsequently refunded per Article 10.3.3 — see below) |
| LD Cap Utilised (%) | 0.0% NET (catch-up refund of ₹55,00,000 processed — all LD refunded) |

SECTION 11 — ACTIVE COMPLIANCE EVENTS

- [LOW] C05: CATCH-UP REFUND TRIGGERED (Article 10.3.3): M-1 LD of ₹55,00,000 to be refunded — SCD achievement confirmed ahead of schedule. — Article 10.3.3

- [LOW] BONUS: EARLY COMPLETION BONUS: Projected Day 698 completion = 32 days early = 1.07 months × 1% = 1.07% of contract value = ₹26,75,000 bonus due. — Article 25.1

- [MEDIUM] C07_IRI: NCR-011 & NCR-012: 2 road sections IRI > 2.5 m/km — resurfacing required before Completion Certificate — Article 11.14

SECTION 12 — RISK ASSESSMENT

| Current Risk Score | 0.06 / 1.00 |
| --- | --- |
| Risk Label | LOW |
| Top Risk Factor #1 | IRI roughness failures on 2 sections — must be resolved before Completion Certificate |
| Top Risk Factor #2 | Final punch list: 1 RFI pending — bridge expansion joint inspection |
| Top Risk Factor #3 | Catch-up refund and bonus calculations need authority verification |
| Forecast: Next Milestone Achievement | PROJECT COMPLETION: Projected Day 698 (2027-02-27) — 32 days ahead of SCD (2027-03-31) |

SECTION 13 — RECOMMENDATIONS & ACTIONS

- POSITIVE: Catch-up refund of ₹55,00,000 for M-1 LD is triggered — process refund within 30 days of Completion Certificate per Article 10.3.3.

- POSITIVE: Early completion bonus of ₹26,75,000 is eligible — confirm final completion date for exact calculation per Article 25.1.

- URGENT: Resurface 2 road sections with IRI > 2.5 m/km (NCR-011, NCR-012) before applying for Completion Certificate.

- Complete pending RFI for bridge expansion joint inspection — clear before certificate.

- Prepare Final Bill including: net LD refund, bonus, retention release (5%), and final measurements.

- Initiate Defects Liability Period (5 years) from date of Completion Certificate.

SECTION 14 — CERTIFICATION

| Reported By | Er. Anand Sharma |
| --- | --- |
| Designation | Junior Engineer (Civil) |
| Verified By (AE/JE) | Er. Meera Iyer (AE) |
| Report Date | 2027-02-03 |
| Engineer-in-Charge Approval | Pending / Approved |