RUNNING ACCOUNT (RA) BILL — No. RA-07

NH-44 Karnataka | Agreement: NHAI/KA/EPC/2025/KA-03

TEST DOCUMENT: Includes LD deduction, payment delay, retention, and TDS — tests Penalty Agent + payment workflow

PART A — BILL DETAILS

| RA Bill Number | RA-07 |
| --- | --- |
| Bill Period | 2025-11-01 to 2025-11-30 (Day 214 Report Month) |
| Bill Submitted Date | 2025-12-05 (by 5th of month — on time per Article 22.1) |
| Verification Deadline (15 days) | 2025-12-20 |
| Payment Release Deadline (30 days) | 2026-01-04 |
| Actual Payment Date | 2026-01-22 — DELAYED by 18 days beyond deadline |
| Interest on Delayed Payment | 18 days × 1%/month = 0.6% × ₹48,50,000 = ₹29,100 payable by Authority per Article 22.2 |

PART B — GROSS CLAIM (Measurements this period)

| Sr. | Item Description | Unit | Qty This Bill | Rate (₹) | Amount (₹) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthwork in Embankment (Km 222–228) | Cum | 18,100 | 180 | 32,58,000 | CMB No. 14 certified |
| 2 | Granular Sub-Base — 200mm (Km 220–223) | Cum | 1,200 | 1,200 | 14,40,000 | CMB No. 15 certified |
| 3 | M30 Concrete (Pier Cap, Bridge at Km 231) | Cum | 290 | 8,800 | 25,52,000 | NCR-002 pending — withheld (see Sec C) |
| 4 | Pile Foundation 600mm (Bridge at Km 231) | RM | 120 | 18,500 | 22,20,000 | CMB No. 16 certified |
|  | GROSS CLAIM (as submitted) |  |  |  | 94,70,000 |  |

PART C — DEDUCTIONS (Applied by Authority's Engineer)

| Sr. | Deduction Head | Basis | Amount (₹) | Clause |
| --- | --- | --- | --- | --- |
| 1 | Retention Money (5% of gross) | 5% × ₹94,70,000 | 4,73,500 | Article 22.3(a) |
| 2 | Income Tax TDS (2%) | 2% × ₹94,70,000 | 1,89,400 | Article 22.3(b) |
| 3 | GST-TDS (2%) | 2% × ₹94,70,000 | 1,89,400 | Article 22.3(c) |
| 4 | BOCW Cess (1% of labour component) | 1% × ₹22,00,000 (est. labour) | 22,000 | Article 22.3(d) |
| 5 | Recovery of Mobilisation Advance (10%) | 10% × ₹94,70,000 | 9,47,000 | Article 22.3(e) |
| 6 | Liquidated Damages — M-1 Delay (Day 204–214, 10 days × ₹25,000/day) | 0.05% × ₹5,00,00,000/100 × 10 days | 2,50,000 | Article 10.3.1 — M-1 missed. Catch-up refund eligible if SCD achieved. |
| 7 | WITHHOLDING — NCR-002 (Concrete failure, M30 Pier Cap) | Full value of failed works withheld | 25,52,000 | Article 11.14 — Payment withheld until NCR-002 closed |
|  | TOTAL DEDUCTIONS |  | 46,23,300 |  |

PART D — NET PAYMENT STATEMENT

| Gross Claim Amount | ₹94,70,000 |
| --- | --- |
| Less: Total Deductions | (₹46,23,300) |
| NET AMOUNT PAYABLE (RA-07) | ₹48,46,700 |
| Amount Certified by Authority's Engineer | ₹48,46,700 — Certified on 2025-12-18 |
| Amount Actually Released | ₹48,46,700 — Released 2026-01-22 |
| Payment Delay | 18 days beyond 30-day deadline (deadline: 2026-01-04, paid: 2026-01-22) |
| Interest Due to Contractor on Late Payment | 18/30 months × 1%/month × ₹48,46,700 = ₹29,080 (to be added to RA-08) |

PART E — CUMULATIVE LD LEDGER (as of RA-07)

| Date | Bill No. | Event | LD This Bill | Cumulative LD | Cap % |
| --- | --- | --- | --- | --- | --- |
| 2025-12-05 | RA-07 | M-1 delay (10 days from Day 204 to Day 214) | ₹2,50,000 | ₹2,50,000 | 1.0% |
| (projected) | RA-08 | M-1 delay (continuing — if no recovery by Day 244) | ~₹7,50,000 | ~₹10,00,000 | ~4.0% |
|  | Max Cap | 10% of ₹25,00,00,000 = ₹2,50,00,000 (Article 10.3.2) |  | ₹2,50,00,000 | 100% |

Note: Catch-Up Refund (Article 10.3.3): If Contractor achieves Scheduled Completion Date on time, all LD deducted above will be refunded without interest within 30 days of Completion Certificate.

| Submitted By (Contractor) Mr. Suresh Patel, MD Horizon Infratech Pvt. Ltd. Date: 2025-12-05 Signature: ________________ | Verified By (AE/JE) Er. Meera Iyer, AE Date: 2025-12-16 Signature: ________________ | Certified By (Authority's Engineer) Er. Pradeep Nair, SE Date: 2025-12-18 Signature: ________________ |
| --- | --- | --- |