MONTHLY PROGRESS REPORT

NH-44 Karnataka | 4-Laning KA-03 | Month 3 Report

TEST SCENARIO A: ON-TRACK PROJECT — No violations, healthy progress

SECTION 1 — PROJECT METADATA

| Project Name | 4-Laning of NH-44 from Km 220 to Km 260 (KA-03) |
| --- | --- |
| Agreement Number | NHAI/KA/EPC/2025/KA-03 |
| Contract Type | EPC — NITI Aayog Model Agreement |
| Contract Value | INR 25,00,00,000 |
| Contractor | M/s. Horizon Infratech Pvt. Ltd. |
| Engineer-in-Charge | Er. Pradeep Nair, Superintending Engineer |
| Reporting Period | 2025-07-01 to 2025-07-31 |
| Day Number (from Appointed Date) | 91 of 730 |
| Scheduled Completion Date | 2027-03-31 |
| Approved EoT Date (if any) | — |
| Revised Completion Date | — |

SECTION 2 — PHYSICAL & FINANCIAL PROGRESS

| Parameter | Planned | Actual | Variance | Status |
| --- | --- | --- | --- | --- |
| Physical Progress to Date (%) | 12.5% | 13.1% | +0.6% | ON TRACK |
| Cumulative Expenditure (₹ Lakhs) | 318.00 | 309.50 | -8.50 | ON TRACK |
| Financial Progress (%) | 12.7% | 12.4% | -0.3% | — |

S-Curve Deviation: +0.6% ahead of planned curve. Accelerating well.

Recovery Velocity Required (% per day): N/A — ahead of schedule

Current Velocity (% per day): 0.144% per day

SECTION 3 — BoQ EXECUTION DATA

| BoQ Item | Unit | Total Qty | Prev Cum. | This Month | Cumulative | % Done |
| --- | --- | --- | --- | --- | --- | --- |
| Earthwork Embankment | Cum | 4,50,000 | 30,500 | 36,200 | 66,700 | 14.8% |
| Granular Sub-Base (GSB) | Cum | 85,000 | 0 | 3,800 | 3,800 | 4.5% |
| M30 Concrete (Bridges) | Cum | 12,000 | 690 | 620 | 1,310 | 10.9% |
| Pile Foundation | RM | 4,200 | 420 | 360 | 780 | 18.6% |
| WMM | Cum | 72,000 | 0 | 0 | 0 | 0.0% |

SECTION 4 — MATERIAL RECONCILIATION

| Material | Opening | Received | Consumed | Closing | Theoretical |
| --- | --- | --- | --- | --- | --- |
| Cement (bags) | 1,350 | 6,200 | 5,890 | 1,660 | 5,900 |
| Steel (MT) | 15 | 62 | 59 | 18 | 60 |
| Bitumen (MT) | 0 | 0 | 0 | 0 | 0 |

SECTION 5 — LABOUR & MACHINERY

| Planned Skilled Labour (daily avg) | 85 |
| --- | --- |
| Actual Skilled Labour (daily avg) | 88 |
| Planned Unskilled Labour (daily avg) | 210 |
| Actual Unskilled Labour (daily avg) | 205 |
| Key Machinery Deployed | 4 Excavators, 3 Tipper Trucks, 1 Concrete Batching Plant, 2 Vibratory Rollers |
| Machinery Idle Days | 0 days |

SECTION 6 — QUALITY ASSURANCE

| Test Type | Material | Conducted | Passed | Failed | Remarks |
| --- | --- | --- | --- | --- | --- |
| Cube Strength (7-day) | M30 Concrete | 8 | 8 | 0 | All passed — avg 22.4 MPa |
| Cube Strength (28-day) | M30 Concrete | 6 | 6 | 0 | All passed — avg 34.1 MPa |
| Field Density Test | Embankment Soil | 6 | 6 | 0 | All ≥ 97% MDD |
| Slump Test | M30 Concrete | 24 | 24 | 0 | Within range |

| NCRs Issued This Month | 0 |
| --- | --- |
| NCRs Pending Closure | 0 |
| RFIs Submitted | 4 |
| RFIs Pending Approval | 1 |

SECTION 7 — EXTERNAL DISRUPTIONS & HINDRANCE DATA

| Working Days in Month | 31 |
| --- | --- |
| Days Lost to Rainfall | 3 |
| Days Lost to Other Hindrances | 0 |
| Daily Rainfall (avg mm) | 8.2 |
| Cumulative Rainfall this Month (mm) | 32.4 |
| Active Force Majeure Claim | None |
| Weather Anomaly Score (IMD) | 0.18 — Within Normal Range |

SECTION 8 — RIGHT OF WAY & UTILITIES

| Total RoW Required (km) | 40.0 |
| --- | --- |
| RoW Handed Over (km) | 38.5 |
| RoW Pending (km) | 1.5 |
| Pending Chainage | Km 241.2 to Km 242.7 — negotiation in progress |
| HT Power Lines Shifted | Yes — Completed |
| Utility Shifting Status | All utilities shifted except 1 water main at Km 228 |
| Tree Felling Clearance | Yes |

SECTION 9 — GFC DRAWING STATUS

| Total GFC Drawings Required | 48 |
| --- | --- |
| GFC Drawings Approved | 38 |
| GFC Drawings Pending | 10 |
| Critical Pending Drawing | Expansion joint details for Bridge at Km 231 — submitted 2025-07-10 |

SECTION 10 — RA BILL & PAYMENT STATUS

| RA Bill Number | RA-03 |
| --- | --- |
| RA Bill Amount (₹ Lakhs) | 82.50 Lakhs |
| RA Bill Submitted Date | 2025-08-05 |
| Previous Bill Payment Received | Yes |
| Previous Bill Payment Date | 2025-07-28 |
| Payment Delay (days) | 0 |
| Cumulative LD Deducted (₹) | ₹0 |
| LD Cap Utilised (%) | 0.0% |

SECTION 11 — ACTIVE COMPLIANCE EVENTS

No active compliance events this reporting period.

SECTION 12 — RISK ASSESSMENT

| Current Risk Score | 0.18 / 1.00 |
| --- | --- |
| Risk Label | LOW |
| Top Risk Factor #1 | GFC Drawings Pending: 10 (moderate — not yet critical path) |
| Top Risk Factor #2 | RoW Pending: 1.5 km (minor — not blocking current work front) |
| Top Risk Factor #3 | Monsoon forecast: normal season — no FM risk |
| Forecast: Next Milestone Achievement | M-1 (Day 204) — ON TRACK for achievement at current velocity |

SECTION 13 — RECOMMENDATIONS & ACTIONS

- Maintain current labour deployment level (88 skilled — above plan).

- Expedite GFC drawing for expansion joint at Km 231 — currently not critical but will become so in Month 5.

- Resolve RoW at Km 241.2–242.7 within next 30 days to prevent future work-front restriction.

- Continue concrete QA testing regime — zero failures maintained, sustain this.

- File RA-03 bill by 2025-08-05 per schedule.

SECTION 14 — CERTIFICATION

| Reported By | Er. Anand Sharma |
| --- | --- |
| Designation | Junior Engineer (Civil) |
| Verified By (AE/JE) | Er. Meera Iyer (AE) |
| Report Date | 2025-08-02 |
| Engineer-in-Charge Approval | Pending / Approved |